## Sheet1
S.No | Date | Area | Discipline | Description of Work Done | Qty | UOM | Supervisor | Ref
1 | 29/07/2026 | Gas Compression Area |  | erected spools at Sec-1 | 26.9 | m | P. Nath | E00002
2 | 10/06/2026 | Gas Compression Area | Piping | erected spools at Sec-2 | 5.7 | m | P. Nath | E00004
3 | 19/06/2026 | Gas Compression Area | Piping | spool fabrication done for Sec-1 | 31 | m | P. Nath | E00009
4 | 16/05/2026 | Gas Compression Area | Piping | spool fabrication done for North Bay | 20 | m | M. Das | E00012
5 | 07/06/2026 | Gas Compression Area | Piping | welding completed Sec-1 | 40 | m | S. Baruah | E00016
6 | 06/05/2026 | Gas Compression Area | Piping | welding completed Sec-4 | 6.6 | m | S. Baruah | E00017
7 | 21/05/2026 | Gas Compression Area | Piping | pressure testing done Sec-2 | 8.3 | m | R. Gogoi | E00020
8 | 07/04/2026 | Gas Compression Area |  | hydrotest completed for line 6"-CW-1021 | 16.9 | m | P. Nath | E00021
9 | 15/04/2026 | Gas Compression Area | Piping | hydrotest completed for line 6"-CW-1021 | 10.7 | m | K. Bora | E00023
10 | 08/04/2026 | Gas Compression Area | Piping | pressure testing done South Bay | 120 | m | A. Saikia | E00027
11 | 30/06/2026 | Gas Compression Area |  | concrete pouring completed for foundation at Sec-1 | 28.3 | m3 | M. Das | E00029
12 | 17/06/2026 | Gas Compression Area | Civil | poured FDN-C-0226 | 40 | m3 | R. Gogoi | E00030
13 | 11/06/2026 | Gas Compression Area | Civil | concrete pouring completed for foundation at Sec-3 | 32.1 | m3 | P. Nath | E00032
14 | 03/07/2026 | Gas Compression Area | Civil | poured FDN-C-0228 | 80 | m3 | M. Das | E00033
15 | 04/06/2026 | Gas Compression Area | Civil | casting done for foundation North Bay | 18.5 | m3 | A. Saikia | E00034
16 | 12/07/2026 | Gas Compression Area |  | excavation completed for foundation Sec-1 | 10.8 | m3 | R. Gogoi | E00036
17 | 20/07/2026 | Gas Compression Area | Civil | excavation finished near CH 12+600 | 3.9 | m3 | R. Gogoi | E00038
18 | 28/06/2026 | Gas Compression Area | Civil | excavation completed for foundation Sec-3 | 40 | m3 | M. Das | E00039
19 | 08/07/2026 | Gas Compression Area | Civil | excavation finished near CH 9+000 | 40.8 | m3 | P. Nath | E00043
20 | 13/04/2026 | Gas Compression Area | Civil | backfill done FDN-C-0243 | 34.3 | m3 | A. Saikia | E00048
21 | 16/05/2026 | Gas Compression Area | Civil | backfilling around foundation Sec-4 completed | 25.9 | m3 | S. Baruah | E00052
22 | 27/05/2026 | Gas Compression Area | Electrical | cable pulled for Sec-4 feeder | 120 | m | P. Nath | E00056
23 | 09/07/2026 | Gas Compression Area | Electrical | cable pulled for South Bay feeder | 60 | m | S. Baruah | E00057
24 | 20/04/2026 | Gas Compression Area | Electrical | cable termination done at Sec-2 | 80 | m | A. Saikia | E00058
25 | 19/05/2026 | Gas Compression Area | Electrical | terminated both ends CBL-EL-0457 | 40 | m | R. Gogoi | E00059
26 | 04/04/2026 | Gas Compression Area | Electrical | tray installation completed Sec-1 | 40 | m | K. Bora | E00061
27 | 22/04/2026 | Gas Compression Area |  | cable tray erection at North Bay | 120 | m | A. Saikia | E00063
28 | 20/04/2026 | Gas Compression Area | Electrical | tray installation completed South Bay | 34.8 | m | M. Das | E00065
29 | 18/04/2026 | Gas Compression Area | Electrical | transformer P-2467 installed and aligned | 39.8 | m | S. Baruah | E00067
30 | 08/07/2026 | Gas Compression Area | Electrical | installed transformer V-2470B | 46.9 | m | A. Saikia | E00073
31 | 22/07/2026 | Gas Compression Area | Instrumentation | loop LP-IN-0775 installed | 1 | nos | R. Gogoi | E00079
32 | 22/05/2026 | Gas Compression Area | Instrumentation | loop LP-IN-0780 checked ok | 1 | nos | P. Nath | E00084
33 | 08/07/2026 | Gas Compression Area | Instrumentation | loop checking completed LP-IN-0783 | 1 | nos | M. Das | E00086
34 | 10/07/2026 | Gas Compression Area | Instrumentation | impulse tubing completed for Sec-1 | 1 | nos | K. Bora | E00088
35 | 24/04/2026 | Gas Compression Area | Instrumentation | impulse tubing done LP-IN-0786 | 1 | nos | P. Nath | E00089
36 | 08/07/2026 | Gas Compression Area | Instrumentation | impulse tubing done LP-IN-0789 | 1 | nos | M. Das | E00092
37 | 15/05/2026 | Gas Compression Area | Static Equipment | vessel K-2491B erected | 1 | nos | A. Saikia | E00097
38 | 07/07/2026 | Gas Compression Area | Static Equipment | vessel V-2494 erected | 4 | nos | P. Nath | E00100
39 | 14/05/2026 | Gas Compression Area | Static Equipment | vessel K-2495 erected | 1 | nos | K. Bora | E00103
40 | 23/04/2026 | Gas Compression Area | Static Equipment | vessel E-2496B erected | 2 | nos | P. Nath | E00104
41 | 01/04/2026 | Gas Compression Area | Static Equipment | grouting completed T-2497A | 4 | nos | A. Saikia | E00105
42 | 27/05/2026 | Gas Compression Area | Static Equipment | aligned exchanger T-2505 | 4 | nos | R. Gogoi | E00112
43 | 17/04/2026 | Gas Compression Area | Static Equipment | aligned exchanger E-2507A | 1 | nos | A. Saikia | E00113
44 | 18/04/2026 | Gas Compression Area | Static Equipment | alignment completed for exchanger at North Bay | 1 | nos | R. Gogoi | E00114
45 | 18/07/2026 | Crude Gathering Station | Piping | spool erection completed for the line Sec-3 | 17.6 | m | K. Bora | E00118
46 | 23/07/2026 | Crude Gathering Station | Piping | spools erected on line 16"-PG-1111 | 13.2 | m | S. Baruah | E00119
47 | 19/05/2026 | Crude Gathering Station | Piping | spools erected on line 8"-PG-1112 | 60 | m | S. Baruah | E00120
48 | 08/07/2026 | Crude Gathering Station |  | spool fabrication in progress Sec-4 | 11.6 | m | M. Das | E00124
49 | 13/07/2026 | Crude Gathering Station |  | fabricated spools 8"-CW-1119 | 60 | m | P. Nath | E00125
50 | 15/05/2026 | Crude Gathering Station | Piping | welding completed Sec-1 | 60 | m | P. Nath | E00127
51 | 23/05/2026 | Crude Gathering Station | Piping | fit-up and welding done on process gas line Sec-3 | 31.4 | m | P. Nath | E00128
52 | 27/05/2026 | Crude Gathering Station | Piping | 8 joints welded on line 6"-PG-1123 | 9.8 | m | K. Bora | E00129
53 | 22/06/2026 | Crude Gathering Station | Piping | pressure testing done Sec-1 | 10.4 | m | S. Baruah | E00132
54 | 16/06/2026 | Crude Gathering Station | Civil | concrete pouring completed for foundation at Sec-3 | 5.8 | m3 | K. Bora | E00144
55 | 01/06/2026 | Crude Gathering Station | Civil | excavation finished near CH 25+900 | 80 | m3 | A. Saikia | E00147
56 | 30/05/2026 | Crude Gathering Station | Civil | excavation completed for foundation Sec-4 | 9.9 | m3 | S. Baruah | E00151
57 | 31/05/2026 | Crude Gathering Station | Civil | excavated pit for FDN-C-0342 | 10.1 | m3 | R. Gogoi | E00152
58 | 19/07/2026 | Crude Gathering Station | Civil | reinforcement fixing done at Sec-2 | 40 | m3 | K. Bora | E00157
59 | 30/05/2026 | Crude Gathering Station |  | backfilling in progress at CH 40+600 | 6.7 | m3 | A. Saikia | E00160
60 | 03/06/2026 | Crude Gathering Station | Civil | backfill done FDN-C-0353 | 5.8 | m3 | S. Baruah | E00162
61 | 04/05/2026 | Crude Gathering Station | Civil | backfilling in progress at CH 23+800 | 55.2 | m3 | A. Saikia | E00165
62 | 30/04/2026 | Crude Gathering Station |  | cable termination done at Sec-1 | 26 | m | M. Das | E00170
63 | 01/04/2026 | Crude Gathering Station | Electrical | transformer installation done at Sec-3 | 30.5 | m | S. Baruah | E00177
64 | 21/06/2026 | Crude Gathering Station | Instrumentation | instruments installed for Sec-2 | 2 | nos | P. Nath | E00180
65 | 19/05/2026 | Crude Gathering Station | Instrumentation | loop LP-IN-0884 installed | 3 | nos | S. Baruah | E00184
66 | 30/05/2026 | Crude Gathering Station | Instrumentation | loop checking completed LP-IN-0892 | 1 | nos | A. Saikia | E00187
67 | 04/06/2026 | Crude Gathering Station | Instrumentation | loop check done for South Bay | 1 | nos | K. Bora | E00189
68 | 28/06/2026 | Crude Gathering Station | Instrumentation | impulse tubing done LP-IN-0893 | 2 | nos | M. Das | E00191
69 | 18/07/2026 | Crude Gathering Station | Instrumentation | tubing installed at Sec-3 | 2 | nos | S. Baruah | E00192
70 | 16/07/2026 | Crude Gathering Station | Static Equipment | grouting done for vessel at Sec-1 | 1 | nos | R. Gogoi | E00203
71 | 22/04/2026 | Crude Gathering Station | Static Equipment | grouting done for vessel at Sec-2 | 1 | nos | M. Das | E00205
72 | 12/07/2026 | Crude Gathering Station | Static Equipment | grouting done for vessel at Sec-3 | 2 | nos | K. Bora | E00206
73 | 16/04/2026 | Crude Gathering Station | Static Equipment | grouting done for vessel at North Bay | 4 | nos | A. Saikia | E00207
74 | 03/06/2026 | Crude Gathering Station | Static Equipment | grouting completed E-2610A | 2 | nos | P. Nath | E00208
75 | 18/05/2026 | Crude Gathering Station | Static Equipment | exchanger alignment done North Bay | 2 | nos | A. Saikia | E00211
76 | 22/05/2026 | Utilities & Flare |  | spools erected on line 16"-FG-1217 | 34.4 | m | A. Saikia | E00213
77 | 24/05/2026 | Utilities & Flare | Piping | spools erected on line 16"-FG-1217 | 22.7 | m | S. Baruah | E00214
78 | 17/07/2026 | Utilities & Flare |  | spool erection completed for cooling water line Sec-2 | 29.9 | m | M. Das | E00216
79 | 15/04/2026 | Utilities & Flare | Piping | spools erected on line 8"-PG-1222 | 9.3 | m | S. Baruah | E00219
80 | 29/05/2026 | Utilities & Flare | Piping | spool fabrication in progress Sec-3 | 3.5 | m | M. Das | E00223
81 | 25/04/2026 | Utilities & Flare |  | fabricated spools 16"-CW-1226 | 12.5 | m | P. Nath | E00227
82 | 18/04/2026 | Utilities & Flare |  | 5 joints welded on line 12"-FG-1231 | 60 | m | M. Das | E00228
83 | 10/07/2026 | Utilities & Flare | Piping | 5 joints welded on line 8"-HC-1233 | 60 | m | K. Bora | E00230
84 | 21/06/2026 | Utilities & Flare | Piping | welding completed South Bay | 40 | m | R. Gogoi | E00231
85 | 16/05/2026 | Utilities & Flare | Piping | hydro testing carried out on cooling water line Sec-2 | 37.8 | m | K. Bora | E00236
86 | 26/04/2026 | Utilities & Flare | Piping | hydro testing carried out on cooling water line Sec-4 | 21.1 | m | R. Gogoi | E00237
87 | 30/05/2026 | Utilities & Flare | Civil | casting done for foundation Sec-2 | 14.4 | m3 | R. Gogoi | E00241
88 | 01/06/2026 | Utilities & Flare | Civil | poured FDN-C-0442 | 11.9 | m3 | S. Baruah | E00242
89 | 15/07/2026 | Utilities & Flare | Civil | poured FDN-C-0443 | 21.3 | m3 | S. Baruah | E00244
90 | 18/07/2026 | Utilities & Flare | Civil | casting done for foundation Sec-3 | 9.2 | m3 | M. Das | E00245
91 | 23/07/2026 | Utilities & Flare | Civil | poured FDN-C-0446 | 60 | m3 | P. Nath | E00250
92 | 16/07/2026 | Utilities & Flare | Civil | excavated pit for FDN-C-0452 | 38.5 | m3 | R. Gogoi | E00257
93 | 19/07/2026 | Utilities & Flare |  | reinforcement fixing done at Sec-4 | 46.4 | m3 | M. Das | E00264
94 | 08/05/2026 | Utilities & Flare | Civil | reinforcement fixing done at South Bay | 9.1 | m3 | S. Baruah | E00268
95 | 11/05/2026 | Utilities & Flare | Civil | reinforcement fixing done at South Bay | 10.9 | m3 | K. Bora | E00269
96 | 25/06/2026 | Utilities & Flare | Civil | backfilling around foundation Sec-2 completed | 31.7 | m3 | P. Nath | E00271
97 | 03/07/2026 | Utilities & Flare | Electrical | cable laying done CBL-EL-0666 | 120 | m | M. Das | E00272
98 | 11/04/2026 | Utilities & Flare | Electrical | cable laying done CBL-EL-0669 | 9 | m | K. Bora | E00277
99 | 20/06/2026 | Utilities & Flare | Electrical | terminations completed CBL-EL-0673 | 7.1 | m | P. Nath | E00281
100 | 26/06/2026 | Utilities & Flare |  | terminated both ends CBL-EL-0673 | 7.3 | m | S. Baruah | E00283
101 | 06/07/2026 | Utilities & Flare | Electrical | tray installation completed Sec-1 | 120 | m | A. Saikia | E00287
102 | 10/06/2026 | Utilities & Flare | Electrical | tray installation completed Sec-3 | 60 | m | P. Nath | E00288
103 | 07/05/2026 | Utilities & Flare | Electrical | transformer installation done at Sec-4 | 120 | m | K. Bora | E00293
104 | 01/05/2026 | Utilities & Flare | Instrumentation | instruments installed for Sec-1 | 1 | nos | A. Saikia | E00295
105 | 09/06/2026 | Utilities & Flare | Instrumentation | loop checking completed LP-IN-0996 | 2 | nos | K. Bora | E00300
106 | 05/04/2026 | Utilities & Flare | Instrumentation | impulse tubing done LP-IN-1001 | 4 | nos | A. Saikia | E00302
107 | 09/05/2026 | Utilities & Flare | Instrumentation | impulse tubing completed for North Bay | 4 | nos | R. Gogoi | E00303
108 | 08/04/2026 | Utilities & Flare |  | vessel erection completed at Sec-1 | 1 | nos | S. Baruah | E00304
109 | 05/04/2026 | Utilities & Flare | Static Equipment | grouting completed V-2713A | 1 | nos | P. Nath | E00310
110 | 11/05/2026 | Utilities & Flare |  | alignment completed for exchanger at Sec-2 | 2 | nos | S. Baruah | E00315
111 | 22/06/2026 | Utilities & Flare | Static Equipment | alignment completed for exchanger at Sec-3 | 1 | nos | R. Gogoi | E00317
112 | 25/06/2026 | Utilities & Flare | Static Equipment | aligned exchanger V-2721 | 1 | nos | A. Saikia | E00318